## Sheet1
BUILD | NO. | CSM BASE SA093538 SN | JTAG | CSM TRAY SA092538 SN | AOT | FULL SYS SA090038 SN | FT | HS_COLD | DEV | TOP 920-9N64K-00LI-TS2 SN | CUST | Station | Failure BIN | Symptom | Next Step | Picture | Picture.1 | At NVIDIA or Foxconn responsibility | Owner | Status | DD | Debug type | Debug start | Aging | Priority
TS2 | 1 | 63265143770003 | PASS | 63265143750001 | PASS | 63265143660006 | PASS | PASS | DEV031615 | MT2635602CAM | PASS | FT | csm_monitoring_under_stress-monitoring_csm_voltage_and_current-FAIL-MEASUREMENT; | csm1_els_brd_ina__read_12v_els_current-Measuring 12V ELS Current | once unit pass FT- > connect for BSP team and share ip Pass after hotfix released |  |  | NV | SPE | Closed
[12 empty] | CUST | test_setup-memory_info-FAIL-MEASUREMENT; | sys_total_ram-Total RAM memory in GB (normalized to 'market' sizes) |  |  |  | NV | SPE | Closed
[12 empty] | CUST | vdd_vout_conf_ult_data_group-vdd_vout_read__vddvoutgetsetflow_vddvoutgetset-ERROR-MTCRError; | read_i2c_block' function failed: device=/dev/mst/192.168.10.20:23108,@dev@mst@dev-i2c-2, i2c_addr=0x33, addr_width=2, reg_addr=0x20c0, size=1 |  |  |  | NV | SPE | Closed
[12 empty] | CUST | mps_group-mps_test-FAIL-MEASUREMENT; | csm1_mps29816_60h_vdd_m_DPC_INFO-Measuring DPC Model and Revision |  |  |  | NV | SPE | Closed
TS2 | 2 | 63265143770002 | PASS | 63265143750002 | PASS | 63265143660004 | FAIL |  |  |  | SKIP | FT | pcie_erors_check_before_stress-x86_pcie_capability_check-FAIL-MEASUREMENT; | csm1_swb_maglan_asic_pcie_pcie_speed-csm1_swb_maglan_asic_pcie pcie speed check | suspected as ASIC issue - NV need verify E6B171_7_4_3 63265143770002 Stay in FOX as master for AOT |  |  | NV | NPI | closed |  | Stay in FOX as master
TS2 | 3 | 63265143770001 | PASS | 63265143750003 | PASS | 63265143660005 | PASS | PASS | DEV031615 | MT2635602CAJ | PASS | FT | csm_monitoring_under_stress-monitoring_csm_voltage_and_current-FAIL-MEASUREMENT; | csm1_els_brd_ina__read_12v_els_current-Measuring 12V ELS Current | Pass after hotfix released |  |  | NV | SPE | Closed
[12 empty] | CUST | verify_params_group-get_cpu_data-ERROR-ValueError; | cpu pn isn't found in page3. list is []. check TOP SA list vs. page3 PN and rev |  |  |  | NV | SPE | Closed
[12 empty] | CUST | vdd_vout_conf_ult_data_group-vdd_vout_read__vddvoutgetsetflow_vddvoutgetset-ERROR-MTCRError; |  |  |  |  | NV | SPE | Closed
[12 empty] | CUST | ERoTs_verification_group-key_revokation_erots_verify-ERROR-ValueError; |  |  |  |  | NV | SPE | Closed
TS2 | 4 | 63265142550005 | PASS | 63265142540001 | PASS | 63265142450008 | PASS | PASS | DEV031616 | MT2638602AH1 | PASS | AOT | enter_livefish_mode-reboot_and_boot_os-ERROR-ABORTED_frontend; | Chiller sustained out-of-range: overall_temp_to_rack=13.5 (limit [16.0, 18.0]) failed 3/3 times | Need to check if the limit is right |  |  | NV | SPE | Closed
[12 empty] | AOT | chiller_init-monitor_chiller_until_ready-ERROR-ValueError; | Chiller did not reach ready state within 1500s. Parameters still out of range: overall_delta_pressure_psi=16.85. Please check chiller connection. | Need to check if the limit is right |  |  | NV | SPE | Closed
[12 empty] | AOT | fiber check fail | ELS3_1+2 all lane TX no power(-327.68) | OFDR check found ELS3 OE5, OE6 all PMF fiber fracture(N-FBK), need to replace new FBK. |  |  | FXV | Angus | Closed
[12 empty] | FT | post_prbs_test_asic_reset-create_mst_devices_chipset-FAIL-MEASUREMENT; | mst_devices_Linkx-MST Linkx device presence | Retest can pass |  |  | NV | SPE | Closed
[12 empty] | CUST | system_boot_group-power_cycle_first_boot-ERROR-Timeout; |  |  |  |  | FXV | TE | Closed
TS2 | 5 | 63265142550004 | PASS | 63265142540002 | PASS |  | FAIL |  |  |  | SKIP | AOT | laser_tests_prerequisites-create_mst_devices_chipset-ERROR-ABORTED_chiller_issue; | Chiller sustained out-of-range: overall_temp_to_rack=18.2 (limit [16.0, 18.0]) failed 3/3 times | Stay in FOX as master for FT |  |  | NV | SPE | Closed |  | Stay in FOX as master
[12 empty] | AOT | laser_tests_prerequisites-create_mst_devices_els-FAIL-MEASUREMENT; | mst_devices_ELS-MST ELS device presence | Retest can pass Reseat ELSFP in the cage for ELS_IND 8 (physical ELS 9) Replaced ELS Board. Failed chiller issue; retesting. OLD ELS Board PASS ICT |  |  | FXV | Mason | Closed
[12 empty] | AOT | laser_tests_prerequisites-linkup_setup-ERROR-ABORTED_chiller_issue; | Chiller sustained out-of-range: overall_delta_pressure_psi=16.92 (limit [17.0, 25.0]) failed 3/3 times | Need to check if the limit is right |  |  | NV | SPE | Closed
[12 empty] | FT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | cpo_collect_restricted-[meas,ei,li,oil,oli,fc,ops,opm,eip,eocl,tp],[eocl:11.05,11,0,21,0,81,250,32.64,4.09,11.05,-100] |  |  |  | FXV | Angus | Closed
[12 empty] | FT | csm_system_gpio-system_gpio_cplds-FAIL-MEASUREMENT; | Have interference between MMC JIG and QSFP JIG in semi-auto. | Stay in FXV as Master |  |  | FXV | Peter | Closed
TS2 | 6 | 63265142550003 | PASS | 63265142540003 | PASS | 63265142450010 | PASS | SKIP | DEV031616 |  | SKIP | AOT | chiller_init-monitor_chiller_until_ready-ERROR-ValueError; | Chiller did not reach ready state within 1500s. Parameters still out of range: overall_delta_pressure_psi=16.79. Please check chiller connection. | Chiller did not reach ready state within 1500s. Parameters still out of range: overall_delta_pressure_psi=16.83. Please check chiller connection. |  |  | NV | SPE | Closed
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | cpo_collect_linkup-[meas,ei,li,oil,oli,fc,opm,eip,eocl,tp,prp,prb],[prp:-23.01,7,0,13,0,49,139.39,12.73,8.71,6.6,-23.01,nan],[prb:nan,7,0,13,0,49,139.39,12.73,8.71,6.6,-23.01,nan],[prp:-22.22,7,0,13,1,49,139.39,12.67,8.77,6.46,-22.22,nan],[prb:nan,7,0,13,1,49,139.39,12.67,8.77,6.46,-22.22,nan],[prp:-20.97,7,0,13,2,49,139.39,12.89,8.55,6.73,-20.97,nan],[prb:nan,7,0,13,2,49,139.39,12.89,8.55,6.73,-20.97,nan],[prp:-20.97,7,0,13,3,49,139.39,12.89,8.55,6.86,-20.97,nan],[prb:nan,7,0,13,3,49,139.39,12.89,8.55,6.86,-20.97,nan],[prp:-20.46,7,1,13,4,50,144.33,12.76,8.83,6.6,-20.46,nan],[prb:nan,7,1,13,4,50,144.33,12.76,8.83,6.6,-20.46,nan],[prp:-20.97,7,1,13,5,50,144.33,12.67,8.92,6.6,-20.97,nan],[prb:nan,7,1,13,5,50,144.33,12.67,8.92,6.6,-20.97,nan],[prp:-23.01,7,1,13,6,50,144.33,12.64,8.95,6.6,-23.01,nan],[prb:nan,7,1,13,6,50,144.33,12.64,8.95,6.6,-23.01,nan],[prp:-23.01,7,1,13,7,50,144.33,12.79,8.8,6.73,-23.01,nan],[prb:nan,7,1,13,7,50,144.33,12.79,8.8,6.73,-23.01,nan],[prp:-20.0,7,2,13,8,51,139.63,12.98,8.47,6.73,-20,nan],[prb:nan,7,2,13,8,51,139.63,12.98,8.47,6.73,-20,nan],[prp:-20.46,7,2,13,9,51,139.63,13.04,8.41,6.73,-20.46,nan],[prb:nan,7,2,13,9,51,139.63,13.04,8.41,6.73,-20.46,nan],[prp:-23.98,7,2,13,10,51,139.63,12.98,8.47,6.73,-23.98,nan],[prb:nan,7,2,13,10,51,139.63,12.98,8.47,6.73,-23.98,nan],[prp:-23.01,7,2,13,11,51,139.63,12.73,8.72,6.6,-23.01,nan],[prb:nan,7,2,13,11,51,139.63,12.73,8.72,6.6,-23.01,nan],[prp:-20.0,7,3,13,12,52,139.21,12.98,8.46,6.73,-20,nan],[prb:nan,7,3,13,12,52,139.21,12.98,8.46,6.73,-20,nan],[prp:-20.0,7,3,13,13,52,139.21,12.86,8.58,6.73,-20,nan],[prb:nan,7,3,13,13,52,139.21,12.86,8.58,6.73,-20,nan],[prp:-20.97,7,3,13,14,52,139.21,12.76,8.68,6.73,-20.97,nan],[prb:nan,7,3,13,14,52,139.21,12.76,8.68,6.73,-20.97,nan],[prp:-20.97,7,3,13,15,52,139.21,12.82,8.62,6.73,-20.97,nan],[prb:nan,7,3,13,15,52,139.21,12.82,8.62,6.73,-20.97,nan],[prp:-23.01,7,4,14,0,53,144.14,12.7,8.89,6.6,-23.01,nan],[prb:nan,7,4,14,0,53,144.14,12.7,8.89,6.6,-23.01,nan],[prp:-23.98,7,4,14,1,53,144.14,12.67,8.92,6.6,-23.98,nan],[prb:nan,7,4,14,1,53,144.14,12.67,8.92,6.6,-23.98,nan],[prp:-20.97,7,4,14,2,53,144.14,12.76,8.83,6.73,-20.97,nan],[prb:nan,7,4,14,2,53,144.14,12.76,8.83,6.73,-20.97,nan],[prp:-20.46,7,4,14,3,53,144.14,12.89,8.7,6.86,-20.46,nan],[prb:nan,7,4,14,3,53,144.14,12.89,8.7,6.86,-20.46,nan],[prp:-20.46,7,5,14,4,54,144.45,12.67,8.93,6.6,-20.46,nan],[prb:nan,7,5,14,4,54,144.45,12.67,8.93,6.6,-20.46,nan],[prp:-20.97,7,5,14,5,54,144.45,12.67,8.93,6.6,-20.97,nan],[prb:nan,7,5,14,5,54,144.45,12.67,8.93,6.6,-20.97,nan],[prp:-19.21,7,5,14,6,54,144.45,12.67,8.93,6.6,-19.21,nan],[prb:nan,7,5,14,6,54,144.45,12.67,8.93,6.6,-19.21,nan],[prp:-19.21,7,5,14,7,54,144.45,12.82,8.78,6.73,-19.21,nan],[prb:nan,7,5,14,7,54,144.45,12.82,8.78,6.73,-19.21,nan],[prp:-23.98,7,6,14,8,55,144.58,12.95,8.65,6.86,-23.98,nan],[prb:nan,7,6,14,8,55,144.58,12.95,8.65,6.86,-23.98,nan],[prp:-21.55,7,6,14,9,55,144.58,12.89,8.71,6.73,-21.55,nan],[prb:nan,7,6,14,9,55,144.58,12.89,8.71,6.73,-21.55,nan],[prp:-20.97,7,6,14,10,55,144.58,12.89,8.71,6.86,-20.97,nan],[prb:nan,7,6,14,10,55,144.58,12.89,8.71,6.86,-20.97,nan],[prp:-21.55,7,6,14,11,55,144.58,12.82,8.78,6.73,-21.55,nan],[prb:nan,7,6,14,11,55,144.58,12.82,8.78,6.73,-21.55,nan],[prp:-20.97,7,7,14,12,56,144.51,12.89,8.71,6.73,-20.97,nan],[prb:nan,7,7,14,12,56,144.51,12.89,8.71,6.73,-20.97,nan],[prp:-21.55,7,7,14,13,56,144.51,12.92,8.68,6.86,-21.55,nan],[prb:nan,7,7,14,13,56,144.51,12.92,8.68,6.86,-21.55,nan],[prp:-20.46,7,7,14,14,56,144.51,12.86,8.74,6.73,-20.46,nan],[prb:nan,7,7,14,14,56,144.51,12.86,8.74,6.73,-20.46,nan],[prp:-20.46,7,7,14,15,56,144.51,12.67,8.93,6.46,-20.46,nan],[prb:nan,7,7,14,15,56,144.51,12.67,8.93,6.46,-20.46,nan],[prp:-23.01,8,0,15,0,57,139.57,12.76,8.69,6.46,-23.01,nan],[prb:nan,8,0,15,0,57,139.57,12.76,8.69,6.46,-23.01,nan],[prp:-22.22,8,0,15,1,57,139.57,12.61,8.84,6.46,-22.22,nan],[prb:nan,8,0,15,1,57,139.57,12.61,8.84,6.46,-22.22,nan],[prp:-21.55,8,0,15,2,57,139.57,12.76,8.69,6... |  |  |  | FXV | Angus | Closed
TS2 | 7 | 63265142550002 | PASS | 63265142540004 | PASS | 63265142450006 | FAIL | SKIP | DEV031616 | MT2638602AH0 | PASS | FT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | cpo_collect_restricted-[meas,ei,li,oil,oli,fc,ops,opm,eip,eocl,tp],[eocl:-1.0,10,4,20,0,77,0,30.95,-327.68,-1,-100],[eocl:-1.0,10,4,20,1,77,0,30.95,-327.68,-1,-100],[eocl:-1.0,10,4,20,2,77,0,30.95,-327.68,-1,-100],[eocl:-1.0,10,4,20,3,77,0,30.95,-327.68,-1,-100],[eocl:-1.0,10,5,20,4,78,0,31.5,-327.68,-1,-100],[eocl:-1.0,10,5,20,5,78,0,31.5,-327.68,-1,-100],[eocl:-1.0,10,5,20,6,78,0,31.5,-327.68,-1,-100],[eocl:-1.0,10,5,20,7,78,0,31.5,-327.68,-1,-100],[eocl:-1.0,10,6,20,8,79,0,31.23,-327.68,-1,-100],[eocl:-1.0,10,6,20,9,79,0,31.23,-327.68,-1,-100],[eocl:-1.0,10,6,20,10,79,0,31.23,-327.68,-1,-100],[eocl:-1.0,10,6,20,11,79,0,31.23,-327.68,-1,-100],[eocl:-1.0,10,7,20,12,80,0,31.37,-327.68,-1,-100],[eocl:-1.0,10,7,20,13,80,0,31.37,-327.68,-1,-100],[eocl:-1.0,10,7,20,14,80,0,31.37,-327.68,-1,-100],[eocl:-1.0,10,7,20,15,80,0,31.37,-327.68,-1,-100],[eocl:-1.0,11,4,22,0,85,0,31.71,-327.68,-1,-100],[eocl:-1.0,11,4,22,1,85,0,31.71,-327.68,-1,-100],[eocl:-1.0,11,4,22,2,85,0,31.71,-327.68,-1,-100],[eocl:-1.0,11,4,22,3,85,0,31.71,-327.68,-1,-100],[eocl:-1.0,11,5,22,4,86,0,31.49,-327.68,-1,-100],[eocl:-1.0,11,5,22,5,86,0,31.49,-327.68,-1,-100],[eocl:-1.0,11,5,22,6,86,0,31.49,-327.68,-1,-100],[eocl:-1.0,11,5,22,7,86,0,31.49,-327.68,-1,-100],[eocl:-1.0,11,6,22,8,87,0,31.08,-327.68,-1,-100],[eocl:-1.0,11,6,22,9,87,0,31.08,-327.68,-1,-100],[eocl:-1.0,11,6,22,10,87,0,31.08,-327.68,-1,-100],[eocl:-1.0,11,6,22,11,87,0,31.08,-327.68,-1,-100],[eocl:-1.0,11,7,22,12,88,0,31.55,-327.68,-1,-100],[eocl:-1.0,11,7,22,13,88,0,31.55,-327.68,-1,-100],[eocl:-1.0,11,7,22,14,88,0,31.55,-327.68,-1,-100],[eocl:-1.0,11,7,22,15,88,0,31.55,-327.68,-1,-100],[eocl:-1.0,6,6,12,8,47,0,31.62,-327.68,-1,-100],[eocl:-1.0,6,6,12,9,47,0,31.62,-327.68,-1,-100],[eocl:-1.0,6,6,12,10,47,0,31.62,-327.68,-1,-100],[eocl:-1.0,6,6,12,11,47,0,31.62,-327.68,-1,-100],[eocl:-1.0,6,7,12,12,48,0,31.39,-327.68,-1,-100],[eocl:-1.0,6,7,12,13,48,0,31.39,-327.68,-1,-100],[eocl:-1.0,6,7,12,14,48,0,31.39,-327.68,-1,-100],[eocl:-1.0,6,7,12,15,48,0,31.39,-327.68,-1,-100],[eocl:-1.0,6,4,12,0,45,0,31.32,-327.68,-1,-100],[eocl:-1.0,6,4,12,1,45,0,31.32,-327.68,-1,-100],[eocl:-1.0,6,4,12,2,45,0,31.32,-327.68,-1,-100],[eocl:-1.0,6,4,12,3,45,0,31.32,-327.68,-1,-100],[eocl:-1.0,6,5,12,4,46,0,31.21,-327.68,-1,-100],[eocl:-1.0,6,5,12,5,46,0,31.21,-327.68,-1,-100],[eocl:-1.0,6,5,12,6,46,0,31.21,-327.68,-1,-100],[eocl:-1.0,6,5,12,7,46,0,31.21,-327.68,-1,-100] | Pass FT - > Pass HS Cold - > redo Adst and change FBK What is the issue? Failed after FT Jig V&V Automation - need report from FXV |  |  | FXV | Angus | Closed |  | FT - optical debug
[12 empty] | AOT | laser_tests_prerequisites-linkup_setup-ERROR-ABORTED_chiller_issue; | Chiller sustained out-of-range: overall_temp_to_rack=15.6 (limit [16.0, 18.0]) failed 3/3 times | Replace ELS BD then retest. |  |  | FXV | Angus | On-going
[12 empty] | FT | csm_system_gpio-system_gpio_cplds-FAIL-MEASUREMENT; | Have interference between MMC JIG and QSFP JIG in semi-auto. |  |  |  | FXV | Tony | On-going
[12 empty] | AOT | els_dmm_burn-els_dmm_burn-ERROR-ABORTED_chiller_issue; |  |  |  |  | FXV | Joy | On-going
[12 empty] | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | ELS14_2 OE28 lane 1 ~2 lane4~11 lane14 MMC109~112 ELS15_1 OE29 lane 4 ~6 MMC114 | Suspected Sagitta burn, ship as it to MTL |  |  |  |  | closed
TS2 | 8 | 63265142550001 | PASS | 63265142540005 | PASS | 63265142450009 | FAIL | PASS | DEV031616 | MT2632603EDF | PASS | FT | laser_tests_prerequisites-create_mst_devices_chipset-ERROR-ABORTED_chiller_issue; | Chiller sustained out-of-range: overall_temp_to_rack=18.3 (limit [16.0, 18.0]) failed 3/3 times | Pass FT - > Pass HS Cold - > Fail FT - > under debug Skip FT - > Staging Cust |  |  | NV | SPE | Closed |  | electrical debug
[12 empty] | FT | fiber_check-create_mst_devices_chipset-FAIL-MEASUREMENT; | mst_devices_Linkx-MST Linkx device presence |  |  |  | FXV | Mason | Closed
[12 empty] | CUST | ERoTs_verification_group-key_revokation_erots_verify-ERROR-ValueError; |  |  |  |  | NV | SPE | Closed
[12 empty] | FT | power_on-validate_low_speed_link_issue_csm1-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 9 | 63665151910002 | PASS | 63665151900011 | PASS | 63765151890004 | FAIL | PASS | DEV032138 | MT263760244W | PASS | CUST | ERoTs_verification_group-key_revokation_erots_verify-ERROR-ValueError; |  | Pass FT - > Fail on Power on Skip FT - > Staging Cust |  |  | NV | SPE | Closed |  | FT - optical debug
[12 empty] | FT | power_on-validate_low_speed_link_issue_csm1-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 10 | 63665151910013 | PASS | 63665151900009 | PASS | 63765151890008 | PASS | PASS | DEV032138 | MT263760244R | PASS | JTAG | 17 : Chameleon6_ASIC1_MP29816_Program_0x60_Rev0400.etf Failed 1 0 1 |  |  |  |  | FXV | Joy | Closed
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  | Observed the SN read from FW doesn't match the lablel. |  |  | FXV | Peter | Closed
TS2 | 11 | 63665151910004 | PASS | 63665151900015 | PASS | 63665151890002 | PASS | PASS |  |  |  | FT | 129 : Chameleon6_interconnect_ic.cvf Failed 1 0 1 |  | high speed failed redo OFDR, change FBK found failed MMC Cocnnector |  |  | FXV | Mason | Closed |  | FT - optical debug
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 12 | 63665151910003 | PASS | 63665151900010 | PASS | 63765151890001 | PASS | PASS |  |  |  | FT | 7 : Run_Authenticator_Win.etf Failed 1 0 1 |  | MMC conyaninmanation, change FBK |  |  | FXV | Joy | Closed |  | FT - optical debug
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | MMC89 high speed fail TX0 | Found MMC defect. Need FBK replacement. |  |  |  |  | Closed
TS2 | 13 | 63665151910001 | PASS | 63665151900007 | PASS | 63665151890006 | PASS | PASS | DEV032138 | MT263760244N | PASS | [8 empty] | Closed
TS2 | 14 | 63465148070006 | PASS | 63765151110002 | PASS | 63665151890003 | PASS | PASS | DEV032138 | MT263760244X | PASS | CUST | ERoTs_verification_group-key_revokation_erots_verify-ERROR-ValueError; |  |  |  |  | NV | SPE | Closed
TS2 | 15 | 63465148070007 | PASS | 63765151110005 | PASS | 63665151890004 | PASS | SKIP | DEV032138 | MT263760244T | PASS | CUST | ERoTs_verification_group-key_revokation_erots_verify-ERROR-ValueError; |  |  |  |  | NV | SPE | Closed
TS2 | 16 | 63665151910015 | PASS | 63665151900017 | PASS | 63765151890006 | PASS | PASS | DEV032138 | MT263760244M | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 17 | 63665151910016 | PASS | 63665151900014 | PASS | 63765151890003 | PASS | PASS | DEV032138 | MT2637602430 | PASS | FT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | [6 empty] | Closed
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 18 | 63665151910017 | PASS | 63665151900018 | PASS | 63765151890002 | PASS | PASS | DEV032138 | MT263760244U | PASS | CUST | chiller_init-initialize_chiller_params-ERROR-UnboundLocalError; | [6 empty] | Closed
TS2 | 19 | 63665151910018 | PASS | 63665151900016 | PASS | 63765151890007 | PASS | PASS | DEV032138 | MT263760244P | PASS | [8 empty] | Closed
TS2 | 20 | 63665151910019 | PASS | 63665151900013 | PASS | 63665151890001 | PASS | PASS | DEV032138 | MT263760244Q | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 21 | 63665151910020 | PASS | 63765151900016 | PASS | 63665151890005 | FAIL |  | DEV032138 |  |  | FT | csm_monitoring_under_stress-monitoring_csm_voltage_and_current-FAIL-MEASUREMENT | csm1_mps29816_2_hvdd_TEMPERATURE-Measuring temperature in Celsius Expected: 20 <= x <= 70, Received: 72.0 | fail on 0.1.16 |  |  | NV | SPE | Closed |  | electrical debug
[12 empty] | FT | fiber_check-create_mst_devices_chipset-FAIL-MEASUREMENT; |  |  |  |  | FXV | Joy | Closed
[12 empty] | FT | csm_monitoring_under_stress-monitoring_csm_voltage and current | csm1_mps29816_2_hvdd_TEMPERATURE\-Measuring temperature in Celsius" |  |  |  | FXV | Joy | On-going |  | FT - optical debug
TS2 | 22 | 63665151910014 | PASS | 63665151900012 | PASS | 63765151890005 | PASS | PASS | DEV032138 | MT263760244V | PASS | CUST | ERoTs_verification_group-key_revokation_erots_verify-ERROR-ValueError; |  |  |  |  | NV | SPE | Closed
TS2 | 23 | 63465148070025 | PASS | 63765151110012 | PASS | 63565151090061 | PASS | PASS | DEV031956-B | MT2638602L9E | PASS | FT | iber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT |  | Waiting NV on-site to debug? fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT |  |  | NV | SPE | Closed |  | FT - optical debug
TS2 | 24 | 63465148070024 | PASS | 63765151110010 | PASS | 63565151090055 | PASS | PASS | DEV031956-B | MT2638602L97 | PASS |  |  |  | MMC system failed, change FBK |  |  |  |  | Closed
TS2 | 25 | 63465148070008 | PASS | 63765151110001 | PASS | 63565151090053 | PASS | PASS | DEV031956-B | MT2635605R7Q | PASS | [8 empty] | Closed
TS2 | 26 | 63465148070011 | PASS | 63765151110006 | PASS | 63565151090005 | PASS | PASS | DEV031956-B | MT2637605ZNC | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 27 | 63465148070017 | PASS | 63765151110004 | PASS | 63565151090062 | PASS | PASS | DEV031956-B | MT2638602L7L | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
[12 empty] | FT | group_pb_button-group_pb_test-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 28 | 63465148070016 | PASS | 63765151110003 | PASS | 63565151090056 | PASS | PASS | DEV031956-B | MT2638602LH7 | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 29 | 63465148070010 | PASS | 63765151110007 | PASS | 63565151090059 | PASS | PASS | DEV031956-B | MT2638602L99 | PASS | FT | mgmt_system_gpio-system_gpio_cplds_without_test_mode-FAIL-MEASUREMENT; |  |  |  |  | FXV | Joy | Closed
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 30 | 63465148070009 | PASS | 63765151110052 | PASS | 63565151090042 | FAIL |  | DEV031956-B |  |  | FT | group_pb_button-group_pb_test-FAIL-MEASUREMENT; | LED cable damamged. | Need to replace cable. |  |  | FXV | Joy | On-going |  | electrical debug
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | cpo_collect_linkup-[meas,ei,li,oil,oli,fc,opm,eip,eocl,tp,prp,prb],[prb:4e-4,8,7,16,12,64,129.59,12.89,8.24,6.73,-2.58,4e-4],[prb:4e-4,8,7,16,13,64,129.59,13.07,8.06,6.86,-2.7,4e-4],[prb:4e-4,8,7,16,14,64,129.59,12.89,8.24,6.73,-2.33,4e-4],[prb:4e-4,8,7,16,15,64,129.59,12.82,8.31,6.6,-3.02,4e-4] | ELS8_16,MMC64 RxP= -2.6,BER=4E-4, Need CSM replacement |  |  |  |  | On-going |  | FT - optical debug
TS2 | 31 | 63465148070014 | PASS | 63765151110050 | PASS | 63565151090058 | PASS | PASS | DEV031956-B | MT2637605ZMK | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 32 | 63465148070015 | PASS | 63765151110051 | PASS | 63565151090060 | PASS | PASS | DEV031956-B | MT2635605R7P | PASS | FT | fiber_check-create_mst_devices_chipset-FAIL-MEASUREMENT; |  |  |  |  | FXV | Joy | Closed
TS2 | 33 | 63465148070013 | PASS | 63765151110055 | PASS | 63565151090044 | PASS | PASS | DEV031956-B | MT2638602LCL | PASS | [8 empty] | Closed
TS2 | 34 | 63465148070012 | PASS | 63765151110011 | PASS | 63565151090064 | PASS | PASS | DEV031956-B | MT2638602L96 | PASS | FT | prog_power_regulators-prog_power_regulators_asics-ERROR-MTCError |  | passed FT and failed BER at HS_cold - shipped |  |  |  |  | Closed
[12 empty] | CUST | system_boot_group-power_cycle_first_boot-ERROR-Timeout; | [6 empty] | Closed
TS2 | 35 | 63465148070018 | PASS | 63765151110054 | PASS | 63565151090054 | PASS | PASS | DEV031956-B | MT2638602LCJ | PASS | [8 empty] | Closed
TS2 | 36 | 63465148070020 | PASS | 63765151110053 | PASS | 63565151090048 | PASS | PASS | DEV031956-B | MT2638602L9A | PASS | FT | reset_button-reset_test-FAIL-MEASUREMENT; |  | MMC port 28 mising , change FBK |  |  | FXV | Joy | Closed |  | FT - optical debug
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | Closed
TS2 | 37 | 63465148070019 | PASS | 63765151110056 | PASS | 63565151090057 | PASS | PASS | DEV031956-B | MT2638602L4H | PASS | [8 empty] | Closed
TS2 | 38 | 63465148070022 | PASS | 63765151110047 | PASS | 63565151090006 | PASS | PASS | DEV031956-B | MT2638602L98 | PASS |  |  |  | passed FT and failed BER at HS_cold - Pass RX no BER |  |  |  |  | Closed
TS2 | 39 | 63465148070023 | PASS | 63765151110009 | PASS | 63565151090050 | PASS | PASS | DEV031956-B | MT2635605R7N | PASS | [8 empty] | Closed
TS2 | 40 | 63465148070021 | PASS | 63765151110008 | PASS | 63565151090004 | PASS | PASS | DEV031956-B | MT2635605R7M | PASS | [8 empty] | Closed
TS2 | 41 | 63465148070005 | PASS | 63765151110013 | PASS | 63565151090046 | FAIL |  | DEV031956-B |  |  | FT | power_on-config_static_ip-ERROR-Exception; |  | under FT 0.1.16 - > high speed fail |  |  | FXV | Joy | On-going |  | FT - optical debug
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | High speed ELS15 OE29 Lane12~15 BER fail | FT - Pass RX - bad BER |  |  | NV | SPE | On-going
TS2 | 42 | 63465148070026 | PASS | 63765151110049 | PASS | 63565151090049 | PASS | PASS | DEV031956-B | MT2638602L7K | PASS | [8 empty] | Closed
TS2 | 43 | 63465148070004 | PASS | 63765151110048 | FAIL |  |  |  | DEV031956-B |  |  | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | ELS14 OE27 lane8~~11 fiber check no power OFDR from ELS14_8L found Sagitta power low and D36 remating no effect. | Re-do Flytake After cleaning, ADST measurement was performed, but the failure symptom remained unchanged 22-Sep : Inspect ADST / FAU36 remating / FBK 01-Oct : Fail on high OE_loss. According to the guidance, if cannot be repaired in other ways, the CSM shall be replaced |  |  | FXV | Peter | On-going |  | AOT- optical debug
TS2 | 44 | 63465148070003 | PASS | 63765151110014 | FAIL | 63565151090003 |  |  | DEV031956-B |  |  | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | ELS8 OE15 MMC57~59 loss High ELS16 OE31 OE32 loss High | PASS AOT - > ELS cage damage; need to replace ELS cage 27-Sep: Replaced ELS board; now failed on MST device on ELS 2 Verify voltage indication on the unit; summarize the history of the unit 01-Oct : ICT Pass - > next promote to JTAG Suspected as Sagita berun |  |  |  |  | On-going
TS2 | 45 | 63465148070027 | PASS | 63765151110015 | PASS | 63565151090045 | PASS | PASS | DEV031956-B | MT2637605ZMH | PASS | FT | initial_setup-chiller_service_configuration-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 46 | 63465148070032 | PASS | 63765151110016 | PASS | 63565151090047 | PASS | PASS | DEV031956-B | MT2637605ZMJ | PASS | FT | mgmt_system_gpio-system_gpio_cplds_without_test_mode-FAIL-MEASUREMENT; |  |  |  |  | FXV | Joy | Closed
[12 empty] | CUST | core_data_group-build_page3-ERROR-ValueError; | TOP Page3 entry not found: PN=920-9N64K-00LI-TS2 Rev=A3 |  |  |  | NV | SPE | Closed
TS2 | 47 | 63465148070031 | PASS | 63765151110017 | PASS | 63565151090051 | PASS |  | DEV031956-B |  |  | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  |  |  |  | FXV | Peter | On-going
TS2 | 48 | 63465148070030 | PASS | 63765151110018 | PASS | 63565151090063 | PASS | FAIL | DEV031956-B | MT2638602L9D | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  | ELS6 OE12 MMC45 -3 ; not good RX power 22-SEP : Mark and move to CUST |  |  | FXV | Peter | Closed |  | FT - optical debug
TS2 | 49 | 63465148070028 | PASS | 63765151110020 | PASS | 63565151090002 | PASS | FAIL | DEV031956-B | MT2638602LCK | PASS | FT | verify_fuses_data-asics_verify_fuses_data-ERROR-ReadTimeout; |  | Pass FT 0.1.16 |  |  | FXV | Joy | Closed
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | ELS3 OE6 channel loss margin fail | passed FT and failed BER at HS_cold - shipped |  |  | FXV | Peter | Closed
TS2 | 50 | 63465148070033 | PASS | 63765151110019 | PASS | 63565151090052 | PASS | PASS | DEV031956-B | MT2635605R7R | PASS | [8 empty] | Closed
TS2 | 51 | 63465148070034 | PASS | 63765151110021 | PASS | 63565151090043 | PASS | PASS | DEV031956-B | MT2638602LFN | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  | Need FBK replacement |  |  |  |  | Closed |  | FT - optical debug
TS2 | 52 | 63465148070002 | PASS | 63765151120030 | PASS | 63765155580003 | PASS | PASS | DEV031955 | MT2638602V82 | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. |  |  | Qual - Eoptolink | NV | SPE | Closed |  | AOT - OptoLink
TS2 | 53 | 63465148070029 | PASS | 63765151120031 | PASS | 63765155580015 | PASS | PASS | DEV031955 |  |  | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. |  |  | Qual - Eoptolink | NV | SPE |  |  | AOT - OptoLink
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT;
TS2 | 54 | 63465148070035 | PASS | 63765151120032 | PASS | 63765155580006 | PASS | PASS | DEV031955 | MT2638602V6D | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. | real OptoLink fail. If yes → swap OptoLink. If the fail flows through ELS, retest a few times to catch instability |  | Qual - Eoptolink | NV | SPE | Closed |  | AOT - OptoLink
TS2 | 55 | 63465148070037 | PASS | 63765151110022 | PASS | 63565151080010 | PASS | PASS | DEV031956-A | MT2638602VTD | PASS |  |  |  | passed FT and failed BER at HS_cold - shipped |  |  |  |  | Closed
TS2 | 56 | 63465148070036 | PASS | 63765151120033 | PASS | 63765155580005 | PASS | PASS | DEV031955 | MT2638602V81 | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. |  |  | Qual - Eoptolink |  |  | Closed |  | AOT - OptoLink
TS2 | 57 | 63465148070041 | PASS | 63765151120028 | PASS | 63765155580001 | PASS | PASS | DEV031955 | MT2638602V6C | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. |  |  | Qual - Eoptolink |  |  | Closed |  | AOT - OptoLink
TS2 | 58 | 63465148070038 | PASS | 63765151120029 | PASS | 63765155580016 | PASS | PASS | DEV031955 | MT2638602VLC | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. |  |  | Qual - Eoptolink |  |  | Closed |  | AOT - OptoLink
TS2 | 59 | 63465148070039 | PASS | 63765151120027 | PASS | 63765155580002 | PASS | PASS | DEV031955 | MT2638602V6E | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. |  |  | Qual - Eoptolink |  |  | Closed |  | AOT - OptoLink
[12 empty] | FT | initial_setup_jig_control-jig_insert-ERROR-JIGControllerException; | [6 empty] | Closed
TS2 | 60 | 63465148070040 | PASS | 63765151120036 | PASS | 63765155580014 | PASS | PASS | DEV031955 |  |  | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. |  |  | Qual - Eoptolink |  |  |  |  | AOT - OptoLink
[12 empty] | FT | power_on-config_static_ip-ERROR-Exception;
TS2 | 61 | 63465148070042 | PASS | 63765151120035 | PASS | 63765155580008 | PASS |  | DEV031955 |  |  | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. | real OptoLink fail. If yes → swap OptoLink. If the fail flows through ELS, retest a few times to catch instability |  | Qual - Eoptolink |  |  |  |  | AOT - OptoLink
[12 empty] | FT | group_pb_button-group_pb_test-FAIL-MEASUREMENT; | LED harness damaged
TS2 | 62 | 63465148070043 | PASS | 63765151120034 | PASS | 63765155580010 | PASS | PASS | DEV031955 | MT2638602V84 | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. | real OptoLink fail. If yes → swap OptoLink. If the fail flows through ELS, retest a few times to catch instability |  | Qual - Eoptolink |  |  | Closed |  | AOT - OptoLink
TS2 | 63 | 63465148070044 | PASS | 63765151110046 | PASS | 63565151080014 | PASS | PASS | DEV031956-A | MT2635605R6E | PASS | CUST | vdd_vout_conf_ult_data_group-vdd_vout_read__vddvoutgetsetflow_vddvoutgetset-ERROR-MTCRError; | [6 empty] | Closed
TS2 | 64 | 63465148070045 | PASS | 63765151110045 | PASS | 63565151080012 | PASS | PASS | DEV031956-A | MT2637605ZGY | PASS | [8 empty] | Closed
TS2 | 65 | 63465148070046 | PASS | 63765151110023 | PASS | 63565151080007 | PASS | PASS | DEV031956-A |  |  | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | [8 empty] | electrical debug
[12 empty] | FT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT;
TS2 | 66 | 63465148070088 | PASS | 63765151110043 | PASS | 63565151080004 | FAIL |  | DEV031956-A |  |  | FT | 130 : Chameleon6_buswire_bus.cvf Failed 1 0 1 |  | under FT 0.1.16 - > electrical debug
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT;
[12 empty] | FT | csm_system_gpio-system_gpio_cplds-FAIL-MEASUREMENT; | csm1_els_brd_cpld___reg__20E2___bit_asic1_fw_rst_-CPLD csm1_els_brd_cpld, Register _20E2, bit asic1_fw_rst_
[12 empty] | FT | fiber_prbs_test-cpo_run_prbs_en-ERROR-ShellException; | Process terminated forcefully | PRBS fail : run - cof -> see matrix is excited when reaching high speed Sep -22 : Reburn manually with FT team - maybe something at the previous partial FT; the FW did not burn correctly. ASK Roi to burn manually - FXV share ip 28-SEP : may be related to temp issue - NV suggests opening CP to investigate |  |  |  |  | On-going |  | FT - Electrical debug
TS2 | 67 | 63465148070048 | PASS | 63765151110024 | PASS | 63565151080013 | PASS | PASS | DEV031956-A | MT2637605ZA0 | PASS | [8 empty] | Closed
TS2 | 68 | 63465148070047 | PASS | 63765151110026 |  |  |  |  | DEV031956-A
TS2 | 69 | 63465148070087 | PASS | 63765151110044 | PASS | 63565151080005 | PASS |  | DEV031956-A |  |  | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT;
TS2 | 70 | 63465148070086 | PASS | 63765151110025 | PASS | 63565151080016 | PASS | PASS | DEV031956-A | MT2637605ZA7 | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 71 | 63465148070085 | PASS | 63765151110028 | PASS | 63565151080008 | FAIL |  | DEV031956-A |  |  | AOT | power_on-burn_os_if_needed_and_boot_os-ERROR-TimeoutError; | Observed short after FBK replacement. |  |  |  | FXV | Joy | On-going
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | cpo_collect_linkup-[meas,ei,li,oil,oli,fc,opm,eip,eocl,tp,prp,prb],[prb:6e-6,5,2,9,8,35,119.38,12.76,8.01,6.46,-2.64,6e-6],[prb:6e-6,5,2,9,9,35,119.38,12.86,7.91,6.6,-2.54,6e-6],[prb:6e-6,5,2,9,10,35,119.38,12.86,7.91,6.6,-2.88,6e-6],[prb:6e-6,5,2,9,11,35,119.38,12.76,8.01,6.46,-2.06,6e-6] | ELS5 OE9 lane8~11 partner_raw_ber 4e-6, Need CSM replacement. After CSM replaced, ELS5 OE9 lane8~11 still no BER. 23-Sep : Looks like swapping WINDO solved the issue - need to investigate and swap in cold retest 23-SEP : retes cold and fail on EO11 8-11 lane - > next cleaning - if after LB it pass can be relased |  |  |  |  | On-going |  | FT - Mech debug
TS2 | 72 | 63465148070049 | PASS | 63765151110027 | PASS | 63565151080015 | PASS | PASS | DEV031956-A | MT2637605ZA1 | PASS | FT | reset_button-reset_test-FAIL-MEASUREMENT; |  | Pass FT 0.1.14 |  |  |  |  | Closed
TS2 | 73 | 63465148070050 | PASS | 63765151120037 | PASS | 63765155580007 | PASS | PASS | DEV031955 |  |  | AOT | fiber_check-create_mst_devices_chipset-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. | real OptoLink fail. If yes → swap OptoLink. If the fail flows through ELS, retest a few times to catch instability
[12 empty] | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT;
TS2 | 74 | 63465148070051 | PASS | 63765151120038 | PASS | 63765155580004 | PASS | PASS | DEV031955 | MT2638602V85 | PASS | AOT | fiber_check-create_mst_devices_chipset-FAIL-MEASUREMENT; | OPT power omonitor out of spec. Use Eoptolink Windu-692-9IAW0-00K0H. Suspect Windu issue. | [5 empty] | Closed
TS2 | 75 | 63765151910003 | PASS | 63765151900010 | PASS | 63665151890007 | PASS | PASS | DEV032138 | MT263760244J | PASS | AOT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 76 | 63765151910005 | PASS | 63765151900011 | PASS | 63665151890011 | FAIL |  |  |  |  | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | cpo_collect_linkup-[meas,ei,li,oil,oli,fc,opm,eip,eocl,tp,prp,prb],[prb:nan,10,3,19,12,76,134.19,12.82,8.46,6.73,-2.67,nan],[prb:nan,10,3,19,13,76,134.19,12.92,8.36,6.73,-2,nan],[prb:nan,10,3,19,14,76,134.19,12.79,8.49,6.73,-2.14,nan],[prb:nan,10,3,19,15,76,134.19,12.76,8.52,6.6,-2.89,nan] | FT - Pass RX - bad BER |  |  |  |  | On-going |  | FT - optical debug
TS2 | 77 | 63765151910004 | PASS | 63765151900009 | PASS | 63665151890012 | PASS | PASS | DEV032138 | MT263760244L | PASS | FT | power_on-burn_os_if_needed_and_boot_os-ERROR-TimeoutError; |  | Pass FT 0.1.16 |  |  |  |  | Closed
TS2 | 78 | 63765151910006 | PASS | 63765151900013 | PASS | 63665151890010 | PASS | PASS | DEV032138 | MT263760244K | PASS | [8 empty] | Closed
TS2 | 79 | 63465148070052 | PASS | 63765151110030 | FAIL | [6 empty] | AOT | fiber_check-create_mst_devices_chipset-FAIL-MEASUREMENT; |  | The issue follow the cage. Need ELS SA replacement | [6 empty] | AOT- optical debug
TS2 | 80 | 63465148070053 | PASS | 63765151110029 | PASS | 63565151080009 | PASS | PASS | DEV031956-A | MT2638602VWK | PASS | FT | high_speed_eth_linkup-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | [6 empty] | Closed
TS2 | 81 | 63465148070054
TS2 | 82 | 63765151910008 | PASS | 63765151900012 | PASS | 63665151890009 | PASS
TS2 | 83 | 63765151910007 | PASS | 63765151900014 | PASS | 63665151890009 | PASS
TS2 | 84 | 63465148070061 | PASS | 63865156220001 | PASS | 63865156210001 | FAIL | [7 empty] | fail on FT - Try to swap windu -> RX is good - partner ber is good may related to UPHY with SERDES team. 23 - Sep: proceed to OFDR scanning |  |  |  |  | On-going
TS2 | 85 | 63465148070062 | PASS | 63865156220002 | PASS
TS2 | 86 | 63465148070001
TS2 | 87 | 63465148070055 | PASS | 63765151110031 | PASS | 63565151090009 63565151090007 63565151090008 63565151090010 | PASS | PASS | DEV031956-B | MT2638602L7M | PASS | [8 empty] | Closed
TS2 | 88 | 63465148070057 | PASS | 63765151110032 | PASS | 63565151090007 | PASS | PASS | DEV031956-B | MT2638602LCH | FAIL | CUST | laser_tests_prerequisites-create_mst_devices_els-FAIL-MEASUREMENT; | mst_devices_ELS-MST ELS device presence | Need to remate ELS then retest FT? 22-Sep : inspect the ELS / latch if fail - connect to CUST for debug 28-SEP : under NV mech team debug
TS2 | 89 | 63465148070059 | PASS | 63765151110033 | PASS | 63565151090008 | PASS |  |  |  |  | FT | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; |  | failed Edge OE under AOT debug - with limit 6 - X - 13 23-Sep : procees and document the wrong serial numbers of the WINDU
TS2 | 90 | 63465148070056 | PASS | 63765151110034 | PASS | 63565151090010 | FAIL |  |  |  |  | FT | initial_setup_jig_control-jig_insert-ERROR-JIGControllerException;
[13 empty] | fiber_check-parse_cpo_data_collect_results-FAIL-MEASUREMENT; | FT fiber check fail,ELS13_25 Lane 0~11 no els input power and lane12~15 IL=12.3dB,ELS14_27 all Lane no els input power 20:51 FT fiber check fail,ELS13_25 Lane 0~11 no els input power and lane12~15 IL=12.3dB | 22-SEP : suspectes as burn saggita 23-SEP: Show degradation - swap ELS and rerun FT debug 10 times . |  |  |  |  | On-going |  | FT - optical debug
TS2 | 91 | 63465148070060 | PASS